## Recommended_GTM
Airests POS — USA-First Go-To-Market Roadmap (Recommended)
Target | USA mature V1 | Plan | 24 weeks / 6 months | Team | 4 members
Service modes | QSR + Fast Casual + Full Service | Pilot | 1 design-partner restaurant | Platform | Windows POS + SaaS
Phase | Weeks | Primary Goal | Launch Deliverables | Key Engineering / Non-Feature Work | Exit Criteria | Priority
Phase 0 — SaaS & Architecture Foundation | 1–3 | Build the product foundation correctly before feature acceleration | Multi-tenant model (tenant → location → register); Windows POS shell; device/register pairing; configurable service modes (QSR/Fast Casual/FSR); US tax/service-charge configuration; roles/PINs + basic clock-in/out; printer/cash-drawer abstraction; core API/data contracts | Tenant isolation; immutable order/payment event model; CI/CD; dev/test/prod environments; secrets/encryption; audit logging; feature flags; monitoring; backups/restore; offline sync architecture designed now; API idempotency/error model | Two test tenants and multiple locations are isolated; register can be provisioned; configuration versioning works; backup/restore tested; core order/tender data model approved | MUST
Phase 1 — Core Restaurant POS | 4–8 | Complete end-to-end in-store restaurant operations for all 3 service modes | Menu/categories/items/modifiers; min/max/forced modifiers; daypart/availability/86; CSV menu import; order lifecycle; dine-in/takeout/pickup/delivery order types; discounts; service charge/auto-gratuity; floor/tables/seats/server transfers; coursing; split/merge checks; tips; cash/external-card tender recording; partial tender; refunds/voids; cash drawer; receipt printing; basic KOT printing; X/Z, sales/tax/tip/void/server reports | Financial ledger and reversal-only corrections; deterministic rounding; concurrency locks; print queue/retry; permission checks; audit reasons; crash recovery for open checks | Order → kitchen → payment → close → report works for QSR, Fast Casual and Full Service; no duplicate settlement; reports reconcile to tender ledger | MUST
Phase 2 — Kitchen, Offline & Operational Resilience | 9–13 | Make the restaurant keep operating under load and connectivity failures | KDS by station; item routing; fire/hold/re-fire; bump/reopen; expo; multi-station conflict protection; ticket timers; printer fallback; offline menu/config cache; offline order taking; local queue; local kitchen/printing continuity; reconnect/sync; conflict handling; basic multi-location store management and reporting | Local-first sync engine; idempotent event replay; dead-letter/recovery queue; health diagnostics; store/device heartbeat; log collection; offline test harness; restore and rollback runbooks | Simulated internet outage does not stop in-store ordering/kitchen flow; reconnect does not duplicate orders; sync conflicts are recoverable; multi-station KDS passes rush test | MUST
Phase 3 — Digital Ordering & Generic Integration Frameworks | 14–18 | Add direct digital revenue and provider-independent integration architecture | Own responsive web ordering; pickup/delivery; store hours; prep-time; order throttling/pause; scheduled orders; order status; basic customer contact/receipt history; generic Payment Adapter (authorize/capture/void/refund/webhook/reconciliation/device abstraction); generic Delivery Aggregator Adapter (menu/store/order/status/cancel mapping, webhooks, retry/manual exception queue); optional QR-to-web/table token if capacity | API gateway/rate limits; webhook signature validation; idempotency keys; adapter contracts; sandbox/mocks; integration observability; accessibility target for public ordering flow; secure PCI boundary so PAN is not stored by Airests | Web order lands in same POS/KDS pipeline; duplicate webhook tests pass; provider adapters can be added without changing core order/payment logic; exception queue is operable | MUST / QR = SHOULD
Phase 4 — Design Partner, Security & Market Readiness | 19–24 | Turn the feature-complete build into a supportable commercial V1 | Design-partner deployment; onboarding wizard; tenant/location/register provisioning; menu import; remote configuration; data export; basic subscription/entitlement control; admin MFA; support diagnostics; training/help content; deployment/rollback procedure; release candidate; customer-facing display on Windows second screen if capacity | Performance/load tests; offline soak tests; backup restore drill; tenant-leakage tests; vulnerability/dependency scanning; PCI DSS v4.0.1-aligned controls for applicable scope; audit retention; incident/support runbooks; production monitoring/alerts; UAT defect burn-down | Design partner completes real service cycles; zero Sev-1 open defects; financial reconciliation signed off; recovery procedures tested; production monitoring/support playbook ready | MUST / CFD = SHOULD
Phase 5 — Post-Launch Expansion | After V1 | Expand capability after launch without delaying USA market entry | Provider-specific payment certification + first live processor; provider-specific DoorDash/Uber Eats/Grubhub connectors or middleware; QuickBooks/accounting; loyalty; gift cards; reservations; customer mobile app; inventory/recipes/vendors; advanced analytics; advanced bar/pre-auth; advanced CRM/marketing; specialized drive-thru workflow; MEA localization (VAT/fiscal/e-invoicing/local payments/Arabic as required) | Public API/partner portal; advanced governance; deeper compliance; regionalization framework | Prioritized from design-partner feedback and sales pipeline | POST-LAUNCH

## Revised_Timeline
24-Week Delivery Timeline — Mature V1
Workstream | Owner Suggestion | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Architecture / SaaS / security | Member 1 | bar: W1 to W3
Windows POS shell + hardware abstraction | Member 2 | bar: W1 to W3
Core data / ledger / APIs | Member 1 + 3 | bar: W1 to W3
CI/CD / monitoring / test automation | Member 4 | bar: W1 to W24
Menu + modifiers + import | Member 2 + 3 | bar: W4 to W6
Orders / tables / server / coursing | Member 1 + 2 | bar: W4 to W7
Billing / tender / refunds / cash drawer | Member 1 + 3 | bar: W5 to W8
Receipt + KOT printing | Member 2 + 4 | bar: W6 to W8
Core reports + reconciliation | Member 3 + 4 | bar: W7 to W8
KDS / routing / expo | Member 2 + 3 | bar: W9 to W12
Offline local store + sync | Member 1 + 4 | bar: W9 to W13
Multi-location admin basics | Member 3 | bar: W11 to W13
Web ordering | Member 2 + 3 | bar: W14 to W17
Generic payment adapter | Member 1 | bar: W14 to W18
Generic aggregator adapter | Member 3 | bar: W14 to W18
Integration mocks + exception console | Member 4 + 3 | bar: W16 to W18
Design-partner rollout / UAT | All | bar: W19 to W22
Hardening / security / performance | All | bar: W19 to W24
Onboarding / docs / support tooling | Member 2 + 4 | bar: W20 to W23
Release candidate + GTM gate | All | bar: W23 to W24

## Feature_Disposition
Existing Workbook — Recommended Reprioritization
Current Tab | Module | Recommendation | New Placement | Launch Priority | Reason
Phase_1 | Tenant & Device Setup (Single Store) | Expand—not single-store only | Phase 0 | MUST | SaaS and multi-location are launch requirements; tenant/location/register hierarchy must exist before feature work.
Phase_1 | Marketplace Sync (Enhanced) | Replace provider names with generic adapter framework | Phase 3 | MUST | Aggregator access/certification is provider-dependent; core should expose a stable adapter contract and exception queue.
Phase_1 | Menu Builder | Keep | Phase 1 | MUST | Core across QSR, fast casual and full service.
Phase_1 | Modifier Logic Advanced | Keep, but focus restaurant-critical rules | Phase 1 | MUST | Forced/min-max modifiers and routing accuracy are critical in QSR/fast casual.
Phase_1 | Order Lifecycle Engine | Keep | Phase 1 | MUST | Core transactional engine.
Phase_1 | Table & Server Transfers | Keep | Phase 1 | MUST for FSR | Needed for full-service target.
Phase_1 | Website Ordering + Payment | Move and merge duplicate | Phase 3 | MUST | Direct ordering is market-relevant, but core POS should stabilize first.
Phase_1 | Floor Plan + Table Setup | Keep | Phase 1 | MUST for FSR | Needed for full-service target; use service-mode config so QSR can hide it.
Phase_1 | Discount Engine | Keep | Phase 1 | MUST | Daily restaurant operation and audit control.
Phase_1 | Service Charges & Auto Gratuity | Keep, remove MEA-specific CGST/SGST wording | Phase 1 | MUST | USA-first engine should be jurisdiction/config driven, not hard-coded to one region.
Phase_1 | Split Billing & Rounding Control | Merge duplicate split-billing rows | Phase 1 | MUST for FSR | One canonical billing allocation engine is enough.
Phase_1 | Cash Drawer Controls | Keep | Phase 1 | MUST | Essential for cash handling and shift reconciliation.
Phase_1 | Refund & Void Handling | Keep | Phase 1 | MUST | Financial control and audit requirement.
Phase_1 | Integrated Payments + Terminal SDK | Generalize | Phase 3 | MUST framework | Build provider-independent payment adapter; actual certification remains provider-specific.
Phase_1 | Tender & Payment Recording | Keep | Phase 1 | MUST | Allows cash and externally processed card tenders during design-partner phase.
Phase_1 | Receipt Customization | Keep basic; defer advanced branding | Phase 1 | MUST basic | Printed receipt, tax/tip/tender and refund information are core; richer branding can wait.
Phase_1 | Basic Loyalty Points | Defer | Post-Launch | POST | User selected loyalty as post-launch.
Phase_1 | Gift Card System | Defer | Post-Launch | POST | User selected gift cards as post-launch and stored value adds payment/compliance complexity.
Phase_1 | Customer Profiles (Basic) | Reduce scope | Phase 3 | SHOULD | Keep order contact/receipt history for direct online orders; full CRM post-launch.
Phase_1 | Backups + Basic Monitoring | Move earlier and expand | Phase 0 + 4 | MUST | Operational requirement, not a late feature.
Phase_1 | Daily Sales + Server/Tax Reports | Keep | Phase 1 | MUST | Restaurant owners need close-of-day and reconciliation from first pilot.
Phase_1 | Basic Table Reservation | Defer | Post-Launch | POST | User selected reservations as post-launch.
Phase_1 | Roles & Permissions + Time Card | Keep | Phase 0/1 | MUST | Basic RBAC, supervisor PIN and clock-in/out are required.
Phase_2 | Customer Ordering App | Defer; web first | Post-Launch | POST | Own responsive website reaches customers without separate iOS/Android app delivery burden.
Phase_2 | KOT Screen + Kitchen Printing | Move earlier | Phase 1/2 | MUST | Kitchen flow is core to restaurant POS; KOT printing before KDS hardening.
Phase_2 | Terminal Reconciliation Reports | Generalize with payment adapter | Phase 3 | MUST framework | Reconciliation is needed, but provider-specific settlement behavior arrives with processor adapter.
Phase_2 | QR Table Self-Ordering | Keep as reuse/stretch | Phase 3 | SHOULD | Can reuse web-ordering engine with table token; do not let it delay mature V1.
Phase_2 | Reservation Deposit Logic / Enhancements | Defer | Post-Launch | POST | Reservations are post-launch.
Phase_3 | Advanced Analytics Dashboards | Defer; retain core reporting only | Post-Launch | POST | Four-person team should prioritize reliability and core reports.
Phase_3 | Advanced Bar Mode / Payment | Defer | Post-Launch | POST | Target includes FSR, but bar-specific pre-auth/tab workflows are a separate specialization.
Phase_3 | CRM Advanced + Marketing | Defer | Post-Launch | POST | Not required for launch.
Phase_3 | Inventory + Recipes + Vendor / Negative Stock | Defer advanced inventory | Post-Launch | POST | Keep simple menu availability/86 now; recipe/vendor costing is substantial scope.
Phase_3 | Multi-Station Race Handling + Expo | Move earlier | Phase 2 | MUST | Needed for a reliable KDS and multi-station kitchen.
Phase_4 | Multi-Branch / Multi-Tenant SaaS | Move to beginning | Phase 0 | MUST | Cannot safely retrofit SaaS tenant isolation after transactional features are built.
Phase_4 | Offline Mode (POS) | Design in Phase 0; implement in Phase 2 | Phase 0 + 2 | MUST | Offline continuity is a competitive baseline and user said it is important.
Phase_4 | 3rd-Party Integrations Marketplace | Split scope | Phase 3 + Post | MUST generic / POST ecosystem | Delivery generic adapter in V1; QuickBooks/accounting and broader marketplace next phase.
Phase_4 | Advanced Permissions + Audit + Compliance | Split minimum vs advanced | Phase 0 + 4 | MUST minimum | Basic RBAC/audit/security from day one; advanced governance hardens before commercial release.

## Launch_Readiness
Commercial V1 Launch Readiness Gates
Workstream | Required Item | Target Phase | Gate / Acceptance | Status
SaaS | Tenant/location/register isolation | P0 | Automated tenant leakage tests pass; store-specific taxes/printers/configs isolated | Planned
Windows POS | Register provisioning + device binding | P0 | New terminal provisioned without developer intervention; last-good config rollback works | Planned
Restaurant Core | 3 configurable service modes | P1 | QSR, Fast Casual, Full Service workflows pass scripted E2E scenarios | Planned
Financial | Immutable tender ledger + reversal model | P1 | No hard-delete financial records; sales/tender/refund totals reconcile | Planned
Kitchen | KOT/KDS routing and recovery | P2 | Rush test with multi-station routing; no duplicate bump/print | Planned
Offline | Order/KDS/printing continuity | P2 | Internet disconnected during live checks; reconnect produces no duplicate/lost orders | Planned
Direct Ordering | Own web ordering to POS/KDS | P3 | One menu source; throttling/pause; order source/status visible end-to-end | Planned
Payments | Provider-independent adapter | P3 | Mock provider proves auth/capture/void/refund/idempotent webhook/reconciliation contract | Planned
Aggregators | Provider-independent adapter | P3 | Mock provider proves menu/order/status/cancel + retry/dead-letter/manual recovery | Planned
Security | PCI-scoped architecture | P0/P4 | No PAN stored; token/provider boundary documented; applicable PCI DSS v4.0.1 controls reviewed | Planned
Reliability | Backup/restore + monitoring | P0/P4 | Restore drill and alerting drill completed; support can diagnose store/device health | Planned
Onboarding | Self-service setup and menu import | P4 | New restaurant can be configured from checklist without engineering changes | Planned
Release | Design partner validation | P4 | Real operating cycle completed; Sev-1=0; known Sev-2 has accepted workaround | Planned
Support | Runbooks + rollback | P4 | Deployment, rollback, offline recovery, printer failure and data restore procedures documented/tested | Planned

## Market_Basis
Market / Standards Basis Used for Prioritization
Market Expectation | Implication for Airests V1 | Evidence
Offline continuity | Treat offline order flow as launch-critical, not Phase 4. | SpotOn highlights automatic offline operation and Square supports offline payments/operations during outages.
Kitchen display + routing | KDS/KOT must be in the launch path for QSR/fast-casual and useful for FSR. | SpotOn and Toast position KDS as a core restaurant operations product.
Direct online ordering | Own web ordering should precede a separate customer mobile app. | Toast and SpotOn offer direct/commission-free ordering integrated with POS/kitchen.
Unified first/third-party orders | Build one order pipeline with adapter-based external sources. | Square markets centralized in-house/online/delivery partner orders; SpotOn supports direct plus 3rd-party integrations.
Multi-location / cloud management | Tenant/location model and remote management belong in the foundation. | Restaurant POS platforms expose multi-location/cloud management as normal operating capability.
Provider-dependent aggregator access | Do not hard-code delivery providers into the core roadmap. | DoorDash Marketplace APIs are approval-limited, supporting a generic adapter + later provider certification approach.
Payment security scope | Keep Airests outside card-data handling where possible; use provider tokenization/hosted/terminal SDK boundaries. | PCI SSC document library identifies PCI DSS v4.0.1 as the current standard.
Offline payment risk | Generic offline POS should not imply generic offline card acceptance. | Square documents provider/hardware-specific offline payment rules, time limits and risk.